## Projects
PROJECT REGISTER — EDIT AND IMPORT BACK
87 projects · the whole register · edit any white column and import this file back · the shaded columns (FTE, Investment, Benefit/yr, ROI, Payback (mth)) are calculated and are ignored on import · Jira identifies the row — do not change it · leave a cell blank to keep what is already there, write TBC to make it unknown
Jira | Project | Programme | Team | Sub team | Objective | PIC | Saving hrs/month | Cash benefit/yr | Soft benefits | FTE | Mandays | CAPEX | OPEX/month | Investment | Benefit/yr | ROI | Payback (mth) | Commit | Status | Start | Due | Remark
FNP-1151#3 | Fixed Asset Retirement & Addition | Fixed asset automation | Accounting | Other division | 2. F&A process automation | Kade | 1238 |  |  | 7.1 | 329 |  |  | 1069202.5389 | 5016578.8806 | 369.2% | 2.5576 | commit | In Progress | 2026-01-01 | 2026-10-31
FNP-88 | Invoice Automation | Billing automation | Accounting | AP (Non-Trade) | 2. F&A process automation | Gun | 716 |  |  | 4.1 | 61 |  |  | 198241.2002 | 2901349.3364 | 1364% | 0.81993 | commit | Done | 2026-01-26 | 2026-04-30
ROW-12 | MVS, TIMs Flag paperless | Trade matching enhancement | Accounting | AP (Trade) | 2. F&A process automation | P'Phen | 176 |  |  | 1 |  |  |  |  | 713180.8425 |  |  | commit | Done | 2026-03-01 | 2026-05-31
FNP-328 | Datacube - AR | Accounting Datawarehouse | Accounting | AR (Cash/Tender/O2O) | 3. F&A Data warehouse | Gun | 175 |  |  | 1 |  |  |  |  | 709128.6786 |  |  | commit | Done | 2025-01-01 | 2026-02-28
ROW-11 | WHT Agent | WHT Agent | Accounting | AP (Trade) | 5. Automation E2E, AI development | P'Phen | 171 |  |  | 1 |  |  |  |  | 692920.0231 |  |  | commit | Done | 2026-01-20 | 2026-06-20
FNP-795 | Import Project - OCR Invoice sent to TIMs for auto matching | Trade matching enhancement | Accounting | AP (Trade) | 5. Automation E2E, AI development | P'Phen | 170 |  |  | 1 | 20 |  |  | 64997.1148 | 688867.8592 | 959.8% | 1.1322 | commit | In Progress | 2026-02-03 | 2026-07-31
ROW-18 | Auto email | B2B Automation | Accounting | AR (B2B) | 5. Automation E2E, AI development | Kade | 160 |  |  | 0.9 | 15 |  |  | 48747.8361 | 648346.2204 | 1230% | 0.90226 | commit | Done | 2026-02-01 | 2026-03-30 | release 1 HC - end of 2025
FNP-212 | LOI Relaunch (Fixed, service and GP) | AR Mall- Automation E2E | Accounting | AR (Mall) | 2. F&A process automation | Gun | 160 |  |  | 0.9 | 45 |  |  | 146243.5084 | 648346.2204 | 343.3% | 2.7068 | commit | Done | 2026-01-26 | 2026-06-20
ROW-33 | Datacube - remianing | Accounting Datawarehouse | Accounting | GL | 3. F&A Data warehouse | Gun | 159 |  |  | 0.9 |  |  |  |  | 644294.0565 |  |  | commit | In Progress | 2026-01-01 | 2026-04-08
ROW-8 | Developing Lease portal - store lease info (Payment and IFRS16) | Lease Portal | Accounting | AP (Non-Trade) | 4. Efficiency and integration | Kade | 112 |  |  | 0.6 | 60 |  |  | 194991.3445 | 453842.3543 | 132.8% | 5.1557 | commit | Done | 2025-09-01 | 2026-02-28
FNP-914 | AR MALL Bank Statement Receipt recheck | AR Mall- Automation E2E | Accounting | AR (Mall) | 2. F&A process automation | P'Phen | 102.4 |  |  | 0.6 | 30 |  |  | 97495.6722 | 414941.5811 | 325.6% | 2.8195 | commit | In Progress | 2026-01-04 | 2026-06-30
FNP-710 | LOI Phase 2 (Annual, Packed, expansion) | AR Mall- Automation E2E | Accounting | AR (Mall) | 2. F&A process automation | P'Phen | 93 |  |  | 0.5 | 15 |  |  | 48747.8361 | 376851.2406 | 673.1% | 1.5523 | commit | Not Start | 2026-07-31 | 2026-11-30
FNP-848 | AR consolidate tender short -over | Retail cash, non-cash automation | Accounting | AR (Cash/Tender/O2O) | 2. F&A process automation | Gun | 85 |  |  | 0.5 | 20 |  |  | 64997.1148 | 344433.9296 | 429.9% | 2.2645 | commit | In Progress | 2026-05-03 | 2026-06-20
FNP-1151 | Fixed Asset Retirement | Fixed asset automation | Accounting | GL | 2. F&A process automation | Kade | 79 |  |  | 0.5 | 17 |  |  | 55247.5476 | 320120.9463 | 479.4% | 2.071 | commit | In Progress | 2026-01-01 | 2026-10-31
FNP-1265 | AP Book Bank OCR | Supplier portal | Accounting | AP (Non-Trade) | 5. Automation E2E, AI development | P'Phen | 70 |  |  | 0.4 | 20 |  |  | 64997.1148 | 283651.4714 | 336.4% | 2.7497 | commit | In Progress | 2026-06-21 | 2026-07-31
FNP-566 | Automail Cash/Tendor/O2O | Retail cash, non-cash automation | Accounting | AR (Cash/Tender/O2O) | 5. Automation E2E, AI development | Gun | 60 |  |  | 0.3 | 15 |  |  | 48747.8361 | 243129.8327 | 398.8% | 2.406 | commit | Done | 2026-02-23 | 2026-06-20
FNP-267 | Supplier Portal OCR | Supplier portal | Accounting | AP (Non-Trade) | 3. F&A Data warehouse | Kade | 57 |  |  | 0.3 | 25 |  |  | 81246.3935 | 230973.341 | 184.3% | 4.2211 | stretch | Not Start | 2026-07-17 | 2026-10-28
FNP-348 | BS/TB Phase 2 | BS/TB Portal | Accounting | GL | 4. Efficiency and integration | Kade | 50 |  |  | 0.3 | 229 |  |  | 744216.9648 | 202608.1939 | -72.78% | 44.0782 | commit | Done | 2025-06-23 | 2026-06-13 | save - GL
FNP-315 | Fixed Asset Transfer | Fixed asset automation | Accounting | GL | 2. F&A process automation | Kade | 48 |  |  | 0.3 | 178 |  |  | 578474.322 | 194503.8661 | -66.38% | 35.6892 | commit | Done | 2026-01-01 | 2026-03-31
FNP-586 | WHT OCR | Trade matching enhancement | Accounting | AP (Trade) | 5. Automation E2E, AI development | Kade | 40 |  |  | 0.2 | 15 |  |  | 48747.8361 | 162086.5551 | 232.5% | 3.609 | commit | In Progress | 2026-05-17 | 2026-09-26
FNP-440 | SmartFins Insight x Genie CHATBOT -- integrate Finance data | CHATBOT | Finance | Central Finance | 5. Automation E2E, AI development | Pol | 32 |  |  | 0.2 | 30 |  |  | 97495.6722 | 129669.2441 | 33% | 9.0226 | commit | In Progress | 2026-08-02 | 2026-07-31
FNP-379 | PL Forecast | Forecasting automation | Finance | Central Finance | 1. Financial | Gun | 32 |  |  | 0.2 | 30 |  |  | 97495.6722 | 129669.2441 | 33% | 9.0226 | commit | In Progress | 2026-04-02 | 2026-08-31 | CTFN = 12 hrs/month Central HQ = 2hrs/month Store OPEX = 4 hrs/month MALL = 4 hrs/month Margin = 2 hrs/month Property = 4hrs/month B2B/O2O/Wholesale = 3 hrs/month
FNP-1431 | Sales Forecast | Forecasting automation | Finance | Sales | 1. Financial | Gun | 32 |  |  | 0.2 | 489.26 |  |  | 1590024.4201 | 129669.2441 | -91.84% | 147.1459 | commit | In Progress | 2026-03-01 | 2026-10-31 | Create opportunity to drive sales, saving coupon for promotion
FNP-1137 | Fixed Asset Addition | Fixed asset automation | Accounting | GL | 2. F&A process automation | Kade | 29 |  |  | 0.2 | 7 |  |  | 22748.9902 | 117512.7525 | 416.6% | 2.323 | commit | In Progress | 2026-03-01 | 2026-10-31
FNP-1067 | Loss making store | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 20 |  |  | 0.1 | 10 |  |  | 32498.5574 | 81043.2776 | 149.4% | 4.812 | commit | In Progress | 2026-01-08 | 2026-09-17 | Save time for data preparation & Analysis (ถ้าทำ data อย่างเดียวจะ save น้อยกว่านี้)
FNP-865 | Shrinkage Automation (Dashboard) — Actual & Forecast | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 20 |  |  | 0.1 | 20 |  |  | 64997.1148 | 81043.2776 | 24.69% | 9.6241 | commit | In Progress | 2026-01-10 | 2026-11-30 | Based on E2E automation (Weekly)
FNP-906 | Billing Note for Local customer | AR Mall- Automation E2E | Accounting | AR (Debt) | 2. F&A process automation | P'Phen | 17 |  |  | 0.1 | 15 |  |  | 48747.8361 | 68886.7859 | 41.31% | 8.4918 | commit | Done | 2026-03-18 | 2026-03-06
ROW-46 | PL Actual store MVP 1 - 4 | Finance Data warehouse | Finance | Channel | 3. F&A Data warehouse | IT | 16 |  |  | 0.1 |  |  |  |  | 64834.622 |  |  | commit | In Progress | 2026-01-01 | 2026-08-31 | ปัจจุบันยังไม่ save เพราะยังไม่ stable
FNP-146 | Weekly Dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 16 |  |  | 0.1 | 20 |  |  | 64997.1148 | 64834.622 | -0.25% | 12.0301 | commit | In Progress | 2026-01-06 | 2026-06-30
FNP-168 | PBI MALL profit bu Unit | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 16 |  |  | 0.1 | 15 |  |  | 48747.8361 | 64834.622 | 33% | 9.0226 | commit | In Progress | 2026-04-17 | 2026-04-06 | 1 hr/week/2BA >> 8hr
FNP-1066 | Fresh loss (Unknown) | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 14 |  |  | 0.1 | 10 |  |  | 32498.5574 | 56730.2943 | 74.56% | 6.8743 | commit | In Progress | 2026-01-08 | 2026-08-31 | Based on E2E (i.e. include interdept/RTV/Delica/Memo/Hub & Spoke) automation weekly, 1st count, mth-end ถ้าไม่ E2E ต้องมาทำ manual เพิ่มก็จะไม่ save แบบนี้
FNP-119 | Transaction Audit (Expense) Dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 12 |  |  | 0.1 | 10 |  |  | 32498.5574 | 48625.9665 | 49.62% | 8.0201 | commit | In Progress | 2026-11-02 | 2026-06-20 | 1 hr/week/3BA >> 12hr
ROW-87 | E-Tax other income in ERP | E-Tax | Accounting | AR - Non Mall | 2. F&A process automation | IT | 11 |  |  | 0.1 |  |  |  |  | 44573.8027 |  |  | commit | In Progress | 2026-06-01 | 2026-09-30
FNP-489 | Boonterm | Retail cash, non-cash automation | Accounting | AR (Cash/Tender/O2O) | 2. F&A process automation | Gun | 10 |  |  | 0.1 | 10 |  |  | 32498.5574 | 40521.6388 | 24.69% | 9.6241 | commit | Done | 2026-02-23 | 2026-06-20
FNP-1065 | Net margin / Gross margin / RTC / Stock Provision by division | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 10 |  |  | 0.1 | 10 |  |  | 32498.5574 | 40521.6388 | 24.69% | 9.6241 | commit | In Progress | 2026-01-07 | 2026-07-31 | มีอยู่แล้วใน P&L เดิม
FNP-1093 | Weekly Sales/Know Loss (KNIME) | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | Pol | 10 |  |  | 0.1 | 5 |  |  | 16249.2787 | 40521.6388 | 149.4% | 4.812 | commit | Done | 2026-02-06 | 2026-07-06 | มีตั้งแต่ปีที่แล้ว (Monday Operation)
FNP-228 | Memo Approval Flow | Accounting Hub automation | Accounting | Central Accounting | 2. F&A process automation | Gun | 9 |  |  | 0.1 | 30 |  |  | 97495.6722 | 36469.4749 | -62.59% | 32.0802 | stretch | Not Start | 2026-01-08 | 2026-08-31
FNP-1064 | P&L for Finance view | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | Gun | 9 |  |  | 0.1 | 10 |  |  | 32498.5574 | 36469.4749 | 12.22% | 10.6934 | commit | In Progress | 2026-03-06 | 2026-07-31 | มีอยู่แล้วใน P&L เดิม Enhancement to align with new P&L Structure
FNP-1092 | O2O monthend automation | Monthend Automation | Finance | FIN O2O | 2. F&A process automation | Pol | 9 |  |  | 0.1 | 5 |  |  | 16249.2787 | 36469.4749 | 124.4% | 5.3467 | stretch | Not Start | 2026-07-18 | 2026-08-31
FNP-127 | Weekly Dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 8 |  |  | 0 | 5 |  |  | 16249.2787 | 32417.311 | 99.5% | 6.015 | commit | In Progress | 2026-01-06 | 2026-06-30 | 1 hr/week/2BA >> 8hr
FNP-167 | Fill in move out Dashboard for all bu | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 8 |  |  | 0 | 10 |  |  | 32498.5574 | 32417.311 | -0.25% | 12.0301 | commit | In Progress | 2026-01-07 | 2026-07-30 | reject
FNP-842 | Utility income by unit by store dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 8 |  |  | 0 | 10 |  |  | 32498.5574 | 32417.311 | -0.25% | 12.0301 | stretch | Not Start | 2026-02-08 | 2026-01-09 | 1 hr/week/2BA >> 8hr
ROW-15 | FX ERP activation | Trade matching enhancement | Accounting | AP (Trade) | 2. F&A process automation | IT | 6 |  |  | 0 |  |  |  |  | 24312.9833 |  |  | commit | In Progress | 2026-06-01 | 2026-09-30 | Mitigate risk, Internal control
ROW-41 | Management APP - PL Forecast (support weekly -PPT) | Forecasting automation | Finance | Central Finance | 4. Efficiency and integration | Gun | 6 |  |  | 0 | 7 |  |  | 22748.9902 | 24312.9833 | 6.875% | 11.2281 | stretch | Not Start | 2026-08-01 | 2026-09-30
FNP-1004 | Unit Register (Azure) | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 6 |  |  | 0 | 5 |  |  | 16249.2787 | 24312.9833 | 49.62% | 8.0201 | commit | In Progress | 2026-01-01 | 2026-07-15 | 0.5 hr/week/3BA >> 6hr
FNP-939 | AP New Report | Trade matching enhancement | Accounting | AP (Trade) | 4. Efficiency and integration | Gun | 5 |  |  | 0 | 15 |  |  | 48747.8361 | 20260.8194 | -58.44% | 28.8722 | commit | In Progress | 2026-05-04 | 2026-06-30
ROW-69 | O2O Management PBI & dashboard | PBI & Dashboard | Finance | FIN O2O | 4. Efficiency and integration | Pol | 5 |  |  | 0 | 10 |  |  | 32498.5574 | 20260.8194 | -37.66% | 19.2481 | commit | In Progress | 2026-06-21 | 2026-07-16
FNP-124 | LFL Dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 4 |  |  | 0 | 7 |  |  | 22748.9902 | 16208.6555 | -28.75% | 16.8421 | commit | In Progress | 2026-01-06 | 2026-06-30 | 0.5 hr/week/2BA >> 4hr
FNP-147 | Tenent Performance Dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 4 |  |  | 0 | 7 |  |  | 22748.9902 | 16208.6555 | -28.75% | 16.8421 | commit | In Progress | 2026-01-08 | 2026-01-09 | 1 hr/week/1BA >> 4hr
FNP-1151#2 | Fixed Asset Retirement | Fixed asset automation | Accounting | AR - Non Mall | 2. F&A process automation | Kade | 3 |  |  | 0 | 1 |  |  | 3249.8557 | 12156.4916 | 274.1% | 3.208 | commit | In Progress | 2026-01-01 | 2026-10-31
FNP-1073 | Automation transaction audit — payroll & store expenses to 3rd parties | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 3 |  |  | 0 |  |  |  |  | 12156.4916 |  |  | nextyear | In Progress | 2026-01-07 | 2026-07-31 | Auto gen report and send to 3rd party (Monthly)
FNP-1116 | DC Monthend Automation | Monthend Automation | Finance | DC | 2. F&A process automation | IT | 3 |  |  | 0 |  |  |  |  | 12156.4916 |  |  | stretch | Not Start
FNP-871 | Store Expense Dashboard - Aligned P&L Costline to New P&L Structure | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 2.5 |  |  | 0 |  |  |  |  | 10130.4097 |  |  | nextyear | In Progress | 2026-01-06 | 2026-07-16 | มีอยู่แล้วใน P&L เดิม Enhancement to align with new P&L Structure
FNP-927 | AP Debit Balance report | Trade matching enhancement | Accounting | AP (Trade) | 4. Efficiency and integration | P'Phen | 2 |  |  | 0 | 7 |  |  | 22748.9902 | 8104.3278 | -64.38% | 33.6842 | commit | Done | 2026-05-04 | 2026-06-20
FNP-157 | Mall PnL - Excel to Databricks Automation | PBI & Dashboard | Finance | Mall | 3. F&A Data warehouse | IT | 2 |  |  | 0 | 2 |  |  | 6499.7115 | 8104.3278 | 24.69% | 9.6241 | commit | In Progress | 2026-06-21 | 2026-06-07 | 0.5 hr/week >> 2hr
FNP-247 | SCB Auto Export | Retail cash, non-cash automation | Accounting | AR (Cash/Tender/O2O) | 2. F&A process automation | Gun | 1 |  |  | 0 | 2 |  |  | 6499.7115 | 4052.1639 | -37.66% | 19.2481 | commit | Done | 2026-01-20 | 2026-02-20
FNP-1072 | OPEX Detail (K.SC Pack) | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 1 |  |  | 0 |  |  |  |  | 4052.1639 |  |  | nextyear | In Progress | 2026-03-06 | 2026-01-08 | Save only time to check LFL/NS/Reconcile
FNP-1074 | Automate stock loss adjustment | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 1 |  |  | 0 |  |  |  |  | 4052.1639 |  |  | nextyear | In Progress | 2026-01-08 | 2026-08-31 | Save ได้ไม่เยอะ เพราะปัจจุบันเราปรับแต่ตัวใหญ่ๆ ถ้า automate ได้ ก็จะเป็น enhancement
FNP-1070 | Fresh Stock Loss | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 0.5 |  |  | 0 |  |  |  |  | 2026.0819 |  |  | nextyear | In Progress | 2026-01-10 | 2026-11-30 | Mainly Enchancement for stock loss analysis
FNP-1071 | Tao Kae P&L | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | Gun | 0.5 |  |  | 0 |  |  |  |  | 2026.0819 |  |  | nextyear | Not Start | 2026-01-11 | 2026-11-30 | Enchancement ช่วยให้น้องเถ้าแก่หยิบ P&L ถูกต้องเวลาไปหยิบเอง
NEW-3 | AYP RPA |  | Accounting | Mall | 2. F&A process automation | P'Phen | 0 |  |  | 0 | 20 |  |  | 64997.1148 | 0 | -100% |  | watch | Not Start
ROW-4 | Invoice Automation - Fine tune and Learning | Billing automation | Accounting | AP (Non-Trade) | 2. F&A process automation | Gun | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | In Progress | 2026-05-01 | 2026-09-30 | Enhance accuracy
ROW-7 | Petty cash app development to verify by HO ACCT | CO APP - Petty cash | Accounting | AP (Non-Trade) | 4. Efficiency and integration | IT | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | In Progress | 2026-01-01 | 2026-08-15 | Audit point to verify Petty cash at HO Accounting
ROW-9 | Key legacy and up-to-date lease info | Lease Portal | Accounting | AP (Non-Trade) | 4. Efficiency and integration | Kade | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | In Progress | 2026-04-01 | 2026-08-31 | Increase man-hour
ROW-10 | PBI & Dashboard - gen auto report (Payment, cash rent) | Lease Portal | Accounting | AP (Non-Trade) | 4. Efficiency and integration | Gun | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Not Start | 2026-10-01 | 2026-12-31 | Mitigate risk
FNP-173 | CSIR Cross Platform Reconcile | Accounting Datawarehouse | Accounting | Central Accounting | 3. F&A Data warehouse | Gun | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | In Progress | 2026-01-28 | 2026-06-20 | Data integrity
FNP-292 | Commercial Margin Chatbot | CHATBOT | Accounting | Central Accounting | 5. Automation E2E, AI development | Gun | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Not Start | 2026-02-03 | 2026-06-20 | AutoCN ( Lotus's deal, Lotus's promotion ), AutoTA
FNP-1424 | CFO Dashboard webapp | CFO Hub | Finance | Central Finance | 4. Efficiency and integration | TBC | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Not Start | 2026-08-01 | 2026-10-31
FNP-877 | Budget Data For New P&L Structure | Forecasting automation | Finance | Central Finance | 4. Efficiency and integration | James | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Done | 2026-02-20 | 2026-06-20 | Data integrity
FNP-836 | Magento Coupon | Margin enhancement | Finance | Central Finance | 5. Automation E2E, AI development | Thapanee | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | In Progress | 2026-02-25 | 2026-06-20
FNP-169 | CTFN Dasboard Restructure (Management report TH, MY, Happitat) | CFO Hub | Finance | CFO Hub | 4. Efficiency and integration | Thapanee | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | In Progress | 2026-01-06 | 2026-07-17
FNP-868 | One Data Source For Stockloss (Knownloss and Unknownloss) | Monthend Automation | Finance | Channel | 1. Financial | James | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Done | 2025-09-18 | 2026-03-29 | มีมานานแล้ว (Monday Operation) ทำเพื่อให้ทุกคนใช้ Stock loss data ตัวเดียวกัน Finance/Operation/BIC
FNP-935 | Dashboard Portal Configuration | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | In Progress | 2026-04-23 | 2026-05-30 | เป็น Portal ให้กดง่ายๆ
FNP-855 | Fresh Loss (Known) + RTC | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Done | 2026-05-01 | 2026-06-20 | มีมานานแล้ว (Monday Operation)
FNP-873 | New Structure P&L Dashboard | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | In Progress | 2026-04-30 | 2026-06-20 | มีอยู่แล้วใน P&L เดิม Enhancement to align with new P&L Structure
FNP-875 | Sale and Knownloss Weekly Dashboard - Add Weekly Sale and Knownloss Budget | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | Done | 2026-01-04 | 2026-06-20 | มีอยู่แล้วใน P&L เดิม Enhancement to align with new P&L Structure
FNP-860 | Payroll Dashboard | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | James | 0 |  |  | 0 |  |  |  |  | 0 |  |  | nextyear | In Progress | 2026-01-09 | 2026-09-29 | Enchancement for payroll analysis & forecast
FNP-1107 | Store Expense for Store/finance revamp (Monday operation) | PBI & Dashboard | Finance | Channel | 4. Efficiency and integration | TBC | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Done | 2026-02-06 | 2026-06-30 | มีมานานแล้ว (Monday Operation)
FNP-1115 | Store Master file centralization (Region, LFL, etc) | Finance Data warehouse | Finance | Channel | 3. F&A Data warehouse | IT | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | In Progress | 2026-07-01 | 2026-07-31 | Enchancement เพื่อให้ทุกทีมใช้ master data ตัวเดียวกัน
FNP-844 | Comparing leasing Mini Super Dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Kade | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | Done | 2026-01-09 | 2026-02-10 | Monitoring Income > Opportunity gain
FNP-171 | Underperforming store dashboard | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 0 |  |  | 0 |  |  |  |  | 0 |  |  | stretch | Not Start | 2026-09-30 | 2026-10-31 | Monitoring Income > Opportunity gain
FNP-108 | 1 Page Summary | PBI & Dashboard | Finance | Mall | 4. Efficiency and integration | Thapanee | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | Done | 2026-01-21 | 2026-06-27 | Monitoring Income > Opportunity gain
FNP-1105 | Automated Margin Database | Finance Data warehouse | Finance | Margin | 3. F&A Data warehouse | Thapanee | 0 |  |  | 0 |  |  |  |  | 0 |  |  | stretch | Not Start | 2026-07-13 | 2026-08-29
FNP-892 | MarginMap cost by item LOTUS -> MAKRO | Margin enhancement | Finance | Margin | 1. Financial | Thapanee | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | In Progress | 2026-03-17 | 2026-06-20
FNP-1104 | Item comparison Makro and Lotuss | Margin enhancement | Finance | Margin | 1. Financial | Thapanee | 0 |  |  | 0 |  |  |  |  | 0 |  |  | commit | In Progress | 2026-06-15 | 2026-07-31
FNP-1446 | ARIP PNL Forecast | IT Project | Finance | Retail Finance | 4. Efficiency and integration | IT | 0 |  |  | 0 |  |  |  |  | 0 |  |  | excluded | Not Start
ROW-6 | Non PO ERP enhancement - paperless | Billing automation | Accounting | AP (Non-Trade) | 2. F&A process automation | IT |  |  |  | 0 | [7 empty] | excluded | In Progress | 2026-06-01 | 2026-09-30
TOTAL | 87 projects as filtered | [5 empty] | 4324.9 |  |  | 24.7 | 1928.26 | 0 | 0 | 6266566.8321 | 17525203.5545
| วางข้อมูล POS declaration POS106 |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.73333 | [11 empty] | Done |  |  | KNIME
| วางข้อมูล POS declaration POS126 |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.73333 | [11 empty] | Done |  |  | KNIME
| วางข้อมูล POS declaration POS136 |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.73333 | [11 empty] | Done |  |  | KNIME
| วางข้อมูลรายการปรับปรุง POS106 |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.1 | [11 empty] | Done |  |  | KNIME
| วางข้อมูลรายการปรับปรุง POS126 |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.1 | [11 empty] | Done |  |  | KNIME
| วางข้อมูลรายการปรับปรุง POS136 |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.1 | [11 empty] | Done |  |  | KNIME
| update unreceived status Shopee |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 2.5 | [11 empty] | Done |  |  | KNIME
| update unreceived status Lazada |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 2.5 | [11 empty] | Done |  |  | KNIME
| update unreceived status TikTok |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.6667 | [11 empty] | Done |  |  | KNIME
| update unreceived status MakroPro |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.83333 | [11 empty] | Done |  |  | KNIME
| update unreceived status Amaze |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.6667 | [11 empty] | Done |  |  | KNIME
| update unreceived status AxtraMall |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.6667 | [11 empty] | Done |  |  | KNIME
| update unreceived status WeChat |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.83333 | [11 empty] | Done |  |  | KNIME
| สรุปออเดอร์ OMS ที่เป็น status canceled แต่มียอดคงค้างที่ checkout report (POS106 / POS126 / POS136) |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1 | [11 empty] | Done |  |  | KNIME
| ทำไฟล์ reconcile ข้อมูลยอดรับเงินจาก TMN & CreditCard กับ rider tips |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1 | [11 empty] | Done |  |  | KNIME
| สรุปข้อมูล detail TrueMoney O2O 3 MID ให้พี่ปู |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.5 | [11 empty] | Done |  |  | KNIME
| MKP Sales Adjustment (BS) by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1 | [11 empty] | Done |  |  | KNIME
| MKP accrued Price diff (Report IT) by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.5 | [11 empty] | Done |  |  | KNIME
| Shopee - MKP payment by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.5 | [11 empty] | Done |  |  | KNIME
| Lazada - MKP payment by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1.5 | [11 empty] | Done |  |  | KNIME
| TikTok - MKP payment by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1 | [11 empty] | Done |  |  | KNIME
| Amaze - MKP payment by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1 | [11 empty] | Done |  |  | KNIME
| AxtraMall - MKP payment by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 1 | [11 empty] | Done |  |  | KNIME
| WeChat - MKP payment by product |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.25 | [11 empty] | Done |  |  | PBI
| O2O monthly sales report |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.083333 | [11 empty] | Done |  |  | PBI
| Summary e-form O2O |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.083333 | [11 empty] | Done |  |  | PBI
| O2O Marketplace ¦ write-off data update |  | Accounting | AR O2O | 2. F&A process automation | Saranrat Lawang | 0.41667 | [11 empty] | Not Started |  |  | PBI
| (Order report form Phoenix) Summary Short-Over Credit Online, Bank Reconcile Credit Online |  | Accounting | AR O2O | 2. F&A process automation | Kamolwan Chasaen | 7.3333 | [11 empty] | Done |  |  | PowerQuery
| (Settlement data) Bank Reconcile QR Payment (ND) |  | Accounting | AR O2O | 2. F&A process automation | Kamolwan Chasaen | 3.6667 | [11 empty] | Done |  |  | PowerQuery
| (Settlement data) Bank Reconcile Credit Online |  | Accounting | AR O2O | 2. F&A process automation | Kamolwan Chasaen | 7.3333 | [11 empty] | Done |  |  | PowerQuery
| (Settlement data) Amaze ODM Reconcile order QR Payment |  | Accounting | AR O2O | 2. F&A process automation | Kamolwan Chasaen | 1.3333 | [11 empty] | Done |  |  | PowerQuery
| (Settlement data) AxtraMall ODM Reconcile order QR Payment |  | Accounting | AR O2O | 2. F&A process automation | Kamolwan Chasaen | 1.3333 | [11 empty] | Done |  |  | PowerQuery
| clean data จาก report payment ของ TikTok เพื่อนำเข้า PBI |  | Accounting | AR O2O | 2. F&A process automation | Wanna Nunim | 1.25 | [11 empty] | Done |  |  | KNIME
| สรุปรายงานตามรูปแบบ payment report TikTok เพื่อส่งต่อให้กับผู้เกี่ยวข้อง |  | Accounting | AR O2O | 2. F&A process automation | Wanna Nunim | 2.5 | [11 empty] | Done |  |  | PBI
| clean data จาก report payment ของ Shopee เพื่อนำเข้า PBI |  | Accounting | AR O2O | 2. F&A process automation | Wanna Nunim | 4.1667 | [11 empty] | Done |  |  | PBI
| สรุปรายงานตามรูปแบบ payment report Shopee เพื่อส่งต่อให้กับผู้เกี่ยวข้อง |  | Accounting | AR O2O | 2. F&A process automation | Wanna Nunim | 2.5 | [11 empty] | In Progress |  |  | PBI
| Report Unmatched order (Lazada/Shopee/TikTok/WeChat) |  | Accounting | AR O2O | 2. F&A process automation | Wanna Nunim | 2.6667 | [11 empty] | Not Started |  |  | KNIME
| Settlement Report-TMN Online(Bank Reconcile) |  | Accounting | AR O2O | 2. F&A process automation | Kuljira Soontornsaratoon | 7.3333 | [11 empty] | Done |  |  | PowerQuery
| Settlement Report QR(SD)(Bank Reconcile) |  | Accounting | AR O2O | 2. F&A process automation | Kuljira Soontornsaratoon | 5.5 | [11 empty] | Done |  |  | PowerQuery
| Rider Tip Data(Bank Reconcile/ShortOver TMN Online) |  | Accounting | AR O2O | 2. F&A process automation | Kuljira Soontornsaratoon | 1.8333 | [11 empty] | Done |  |  | PowerQuery
| Order Report from Phoenix Data(Bank Reconcile/ShortOver TMN Online&QR(SD)) |  | Accounting | AR O2O | 2. F&A process automation | Kuljira Soontornsaratoon | 5.5 | [11 empty] | Done |  |  | PowerQuery
| Detail adjustment BS of marketplace (SKU, Allocate) |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 1 | [11 empty] | Done |  |  | PBI
| POS Declaration Map Checkout |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 4 | [11 empty] | Done |  |  | KNIME
| Detail adjustment BS of Tender Missing Amaze & AxtraMall ODM |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 0.16667 | [11 empty] | Done |  |  | KNIME
| Detail adjustment BS of Tender Missing Amaze & AxtraMall MKP |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 0.16667 | [11 empty] | Done |  |  | KNIME
| Reconcile pickup สลับระหว่าง POS106,126,136 |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 1 | [11 empty] | Done |  |  | PBI
| Allocate fee by store by date Amaze ODM for JV record |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 0.25 | [11 empty] | Done |  |  | KNIME
| Payment Amaze ODM |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 2.5 | [11 empty] | Not Started |  |  | PBI + KNIME
| Payment AxtraMall ODM |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 2.5 | [11 empty] | Not Started |  |  | PBI + KNIME
| Payment Amaze & AxtraMall MKP |  | Accounting | AR O2O | 2. F&A process automation | Kawinlada Prompakdee | 2.5 | [11 empty] | Not Started |  |  | PBI + KNIME
| Lotus’s Online App - Checkout invalid (IT Issue) - รวมข้อมูลจาก Excel หลายไฟล์ |  | Accounting | AR O2O | 2. F&A process automation | Wannaporn Dokbua | 2.5 | [11 empty] | Done |  |  | PowerQuery
| Bank reconcile TMN atDoor (Ondemand & Scheduled) - clean data เพื่อ reconcile ต่อใน Excel |  | Accounting | AR O2O | 2. F&A process automation | Wannaporn Dokbua | 3.3 | [11 empty] | Done |  |  | PowerQuery
| Compare ReSa vs POS106 |  | Accounting | AR O2O | 2. F&A process automation | Wannaporn Dokbua | 0.33333 | [11 empty] | Not Started |  |  | PBI
| Lotus’s Online App - Tender missing ( Checkout & ReSa) |  | Accounting | AR O2O | 2. F&A process automation | Wannaporn Dokbua | 0.5 | [11 empty] | Not Started |  |  | PBI
| Auto JV - BBL | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Choowit S | 2 | [11 empty] | Not Start |  |  | PBI
| Auto JV - BBL QR CPFM | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Choowit S | 12 | [11 empty] | Done |  |  | PBI
| Auto JV - Grab | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Treerat O | 4 | [11 empty] | Done |  |  | PBI
| Auto JV - Line Man | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Treerat O | 2 | [11 empty] | Done |  |  | PBI
| Auto JV - Shopee | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Treerat O | 2 | [11 empty] | Done |  |  | PBI
| Vending Machine | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Treerat O | 18 | [11 empty] | Inprogress |  |  | PBI
| Reconcile Mart App | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Treerat O | 4 | [11 empty] | Inprogress |  |  | PBI
| Fraud | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Janyaporn S | 4 | [11 empty] | Not Start |  |  | PBI
| Refill QR | Retail cash, non-cash automation | Accounting | AR Retail | 2. F&A process automation | Supaporn J | 4 | [11 empty] | Inprogress |  |  | PBI